## Slide 1
Playwright Migration — 600 Automated Tests
3 – 3.5 weeks
with 3 QA engineers • ~30–35 person-days
Includes incorporating the new design-system changes
All 600 tests migrated — none dropped
Week 1
Setup + pilot
Weeks 2–3
Migration at pace
Final days
Verify + switch over
Zero test loss
Existing scenarios reused as-is, verified automatically
AI-accelerated
AI converts, automated checks verify, engineers review
Measured, not guessed
Week-1 pilot confirms the pace on real tests
Indicative estimate — POC in progress will refine it; committed date set at the Week-1 checkpoint.

## Slide 2
Next Phase — Automating 600 New Tests
~4 weeks
with 3 QA engineers • ~40 person-days
Starts immediately after migration — on the same framework
Manual test steps already written; scenario design is done
Framework already built
No setup — pipeline, components and process are in place
Heavy reuse
Most new tests reuse existing steps — little new code needed
AI writes the first draft
Test steps drafted from the existing manual test cases
Overall roadmap
Weeks 1–3.5
Migrate 600 tests
Weeks 4–7.5
Automate 600 new tests
~2 months
1,200 tests on one modern stack
Indicative estimate — refined by the POC and a reuse analysis at the start of the phase.

## Slide 3
What We Already Have in Place
This plan builds on existing assets and work already underway — not a standing start
POC already underway
Playwright POC is running today, led by the QA lead — giving us real data to refine these estimates before work begins.
Playwright running in production
A Playwright + TypeScript framework is already built and operating on our second product — proven in daily use.
Tooling already integrated
Playwright MCP server connected, with Allure and Monocart reporting already wired into the POC repo.
Pipeline pattern already built
A comparable Jenkins pipeline is already delivered for another application — the CI design is proven, not theoretical.
Full context on the 600 tests
These scenarios, their tags, data and known quirks are already understood in-house — no knowledge-transfer ramp needed before starting.
Plan and process documented
Execution plan, daily conversion playbook, AI-assisted process and CI quality gates are written and ready to follow from day one.
Proposed next step: 3 QA engineers dedicated to the ~2-month programme — migration in 3–3.5 weeks, new automation in ~4 weeks — with a Week-1 checkpoint that converts these indicative estimates into committed dates backed by real data.